## Sheet1
Date | Project Progress(Bank Application)
2021-01-20 | Initiated Spring Boot Bank Application.Created Account,TransactionLog,Employee POJOs,Dao,DaoImpl,Service and serviceImpl.
2021-01-21 | Added REST end points for Account and TransactionLog.Initiated Angular front end application and created a page to display all accounts.
2021-01-22 | Created Crud front end to display all accounts.create update,view,create-account,delete account components and created withdraw,deposit,transfer components in front end.
2021-01-25 | Added Security end point in Spring boot and configured security in Angular front end.